Evaluative Activity Commentary

University of Bath (SW Spoke)

1st August 2011 – 31st January 2012

Introduction

The past six months has been a period of substantial activity for the SW Spoke’s projects. In addition, this period saw the introduction of a number of new projects, set up through the Practice Transfer Adopter scheme, and through a new strategic initiative that has enabled the Spoke, drawing on experiences from its regional CoP project, to instigate a national WP project to strengthen existing, and develop new, models for HEI-third sector collaborations in the field of STEM outreach.

The Spoke has set up a number of mechanisms to enable oversight, support, dissemination, evaluation, sustainability and impact for its activities; as outlined below, these continue to prove effective. The SW Regional Director would however like to pay particular tribute to the work of the SW Project Officers in this regard; it is clear that project leads find their active support invaluable in attending steering group meetings, providing advice and guidance to project leads, fostering and encouraging collaboration, providing information and spreading good practice between projects, and providing frameworks for projects to maximise their sustainability, encourage peer review and reflection and demonstrate the impact of their activities.

Specific Aim 1: Package, transfer and embed outcomes from Pilot Projects into core activities within the Higher Education sector.

Two of the SW Spoke’s projects are specifically designed to embed outcomes from Pilot Projects into HEIs’ core activities: ‘Extending the Use of Spectroscopy in a Suitcase’ (SIAS) and ‘Design a Fireworks Show – Using Context and Problem-Based Learning in Chemistry’ (based on the IoP’s Ashfield Music Festival model). Both projects are being led by the University of Bath but involve collaboration with the University of Exeter and the University of Plymouth, as well as with a range of local schools and employers.

Both these projects are progressing well. New SIAS materials have been developed and were trialled in November 2011 in three schools, involving 60 students in all.  Feedback was captured from the school students and teachers which will feed into the final evaluation. More trials are planned for February which will utilise postgraduates to deliver the materials and these will provide an opportunity to collect further feedback from participants. The universities of Reading and Northumberland have also received money from the RSC to produce new SIAS resources and the project team at the University of Bath plans to coordinate a dissemination event with them in June 2012.

Over the past 6 months, the Project Coordinator for the Design a Fireworks Show project has engaged fireworks manufacturers in collating a variety of exemplar materials such as risk assessments and model contracts, as well as photographs and videos. These have been used to inform the context and problem-based learning resources which are now written and ready for use in the spring semester.

Specific Aim 2: Undertake activities to widen participation within the STEM disciplines at university level by supporting HEIs to work with those currently within the School and FE sectors.

A project led by the University of Exeter to develop a sustainable SW Community of Practice (CoP) for STEM WP and Outreach practitioners has continued to make good progress and its success has informed a larger national CoP project. The CoP held its second event in November at @Bristol Science Learning Centre (cross reference Specific Aim 5 for full details of the event and its outcomes). Several individuals have taken the opportunity to benefit from the project’s peer review funding opportunities and plans are already underway for the project’s final event in April 2012. The CoP’s project coordinator has undertaken comparative research of all the SW HEIs’ access agreements and from this, will produce a case study guide on what HEIs are doing in the field of widening participation. The project’s sustainability lies both in its absorption into the larger national CoP project and in its success in spreading its good practice to three other HEIs through the Practice Transfer Adopters’ Scheme. In addition, the project has inspired a proposal for a new Maths module which will involve students undertaking 20 hours of voluntary outreach and then reflecting on their experience.

In collaboration with the University of Bristol, the IoP and the University of the West of England, the University of Bath is leading a project investigating different models of STEM communication. Research that the project undertook of students’ motivations prior to undertaking STEM communications was discussed and presented at a project event in November 2011 (cross reference Specific Aim 5 for full details of the event and its outcomes). This research is now continuing to add a longitudinal dimension to findings. As a direct result of the project (and aiding its sustainability), a ‘Communicating Science’ module has been launched for first year undergraduate students at the University of Bristol, as have undergraduate ‘Physics Communicators’ and ‘Maths Communicators’ modules at the University of Bath. Work is also underway on devising a Guide to STEM Communication models which will be presented at a workshop in May. Project leads are currently training another 40+ students to undertake a range of STEM communicator activities across February to May 2012, with recruitment and training procedures improved due to findings from the project.

The ‘Becoming a STEM Enthusiast’ project (led by the University of Exeter, with input from the University of Plymouth and Bournemouth University), aims to enhance the information, advice and guidance provided to students considering HE level study, through the production of a series of video vignettes in which both students and staff talk about the rewards, challenges and day-to-day experiences of learning and teaching within their discipline. A total of 32 video vignettes have now been produced and hosted on Vimeo and the project web-pages. Vignettes range from 30 seconds to 10 minutes in length and include the thoughts, opinions and experiences of a range of STEM academics and students. The videos can be used in both schools outreach (answering questions like ‘Why Study Engineering?’) and in academic staff development (covering issues such as research-led teaching and active learning). News of the videos has been disseminated through: the Hub, regional spoke contacts, the South West Educational Developers’ Forum, the IMA, the IoP and STEMNET. This has resulted in 512 hits on the video web-pages. An academic staff developer at the University of Southampton commented: ‘I found these short snippets on research-led teaching very inspiring and would like to show them as part of our Postgraduate Certificate in Academic Practice (PCAP) at the University of Southampton.’ The sustainability of the videos will lie in their adoption by institutions in this way and also, through Exeter’s use of them in both their outreach and ‘Learning and Teaching in HE’ programmes.

A further project being led by the University of Exeter (in collaboration with Devon Education Business Partnership, Graphic Science, the University of Plymouth, and the University of Bath) looks to enhance the employability of STEM student ambassadors. Having developed and delivered employability skills training for some 48 student ambassadors, the project team has now produced ‘train the trainers’ materials (available online, to train existing student ambassadors in delivering employability skills training to new student ambassadors. 15 students have received the ‘train the trainers’ material and will be involved in the coming months with delivering employability skills training to a new batch of student ambassadors. The training materials are going to be used by STEMNET into the future whilst Exeter, Plymouth and Bath universities have now embedded the training into their annual training cycle for student ambassadors. Project partners are currently collating case studies of students who have been involved in the training to capture the benefit and impact of it. These case studies will be published and disseminated in a booklet.

A project led by the University of Bristol in conjunction with Lighting Up Learning Ltd (a learning and development consultancy), Graphic Science (a STEMNET contract holder) and the UK School Seismology Project is looking at up-skilling academics and postgraduate students in the delivery of effective outreach interventions to Key Stage 1 – 3 students. Following two training sessions that attracted 25 participants, a further two were run attracting similar numbers. Out of these, volcano and earthquake workshops have been designed for differing key stage levels (these workshops and the training sessions are available online. Volunteers are currently being trained to deliver the workshops at a variety of schools until Easter 2012. The project has also produced an online Guide to Public Engagement which has been promoted through: the Hub, the IMA, the IoP, the NCCPE and around regional contact lists. This has resulted in 184 hits to the guide’s web-page. Discussions are underway with the Hub to see whether a hardcopy of the Guide could be produced to enhance project sustainability. That sustainability has already been enhanced by the project being included in the PTA process (resulting in 6 adopters buying in to the project) and the project lead receiving requests from a range of other STEM departments to deliver the training to academics.

Coordinated by Bournemouth University, a project into the enhancement of transition and induction experiences for WP STEM students has continued apace. The project delivered the second in a series of four regional seminars at the University of the West of England on 23rd November 2011 (cross reference Specific Aim 5 for full details of the event and its outcomes). Following on from the first seminar in June 2011 and resultant JISCMail discussions, the model of Maths Cafés has been promoted widely by the project and adopted by the University of Bath. In addition, the project lead and coordinator have undertaken 6 interviews with STEMNET ambassadors in order to tap into the unique insights that they have formed from working with school students in an informal setting. The interviews have raised a number of recurrent themes and challenges concerning the transition from school to HE STEM study. Findings from this research will be shared with STEMNET and used to inform the development of institutional guidelines for transition.

A project to develop guidance for good practice in inclusive laboratory provision for visually impaired students has undertaken questionnaires of students with VI in order to identify some of the challenges related to HE STEM study; collated a series of useful national resources; produced a blog of ‘Tech Tips for Students’  and a document on the ‘Differences in VI’. In March 2012, an outreach event will be held at the University of Bath for students with VI at which they will have an opportunity to undertake STEM activities and to feed into a focus group about studying STEM at University with a visual impairment. User case studies are now being developed, together with a practical guide on inclusive laboratory practice for STEM academics and a virtual training package on inclusive teaching for use by academic staff developers in PGCAPP courses. In particular, the latter two outputs will enhance the sustainability of the project.

Drawing on experiences from its regional CoP project, the Spoke has now instigated a national WP project to strengthen existing, and develop new, HEI-third sector collaborations in the field of STEM outreach by establishing both national and regional CoPs. Following a meeting at Bath on 15th November between 8 national third sector organizations and the SW Spoke, AccessHE (an educational charity based in London) agreed to take lead of the project. A national CoP will form and meet three times before July 2012 (the first meeting is on 28th February) with third sector partners receiving funding to develop and trial STEM outreach activities with HEIs (bids for this activity are due 6th February).

Specific Aim 3: Initiate Higher Education curriculum developments focusing upon course delivery and design, student support, and knowledge and skills.

Bournemouth University is leading a project in collaboration with the University of Bath, the IMA, UWE and STEMNET to research the particular benefits of Peer Assisted Learning (PAL) for students studying HE STEM programmes. The second of four planned seminars has been held (and an associated briefing paper produced) to provide national context (cross reference Specific Aim 5 for full details of the event and its outcomes). A literature review of models of online PAL has been completed by UWE, running alongside a pilot of online PAL at the same institution; UWE will be taking a blended approach to PAL into the future. A focus group of PAL leaders took place at UWE back in November 2011, the results of which will be supplemented by interviews with PAL leaders at Plymouth University on 30th January 2012 (these interviews will be recorded as part of the project’s creative learning journey). Outcomes from all this research will feed into the development of institutional guidelines for the implementation of PAL for STEM disciplines.

The ‘Developing a student-led employability audit toolkit for HE STEM curricula’ project being led by the University of Exeter has attracted a diverse steering group consisting of: University of Exeter academics, central services staff and students; Devon Education Business Partnership and seven STEM employers. Over the summer of 2011, a focus group of 12 mathematics and engineering students audited the employability skills elements of their degree programmes, a process that was captured as part of the project’s creative learning journey. Students commented: ‘It's been a very productive 6 weeks and we feel the contributions we have made will be valuable in improving the degree programme;’ ‘These weeks have been fun and I hope that some of the changes that we recommended are implemented, either for the coming academic cycle or the next.’ The students produced a 30 page report for a ‘learning and teaching’ committee which included a proposal for a new Maths Group Work module. This ran successfully across the Autumn semester (with a sign-up of 24 students), and will be continued into the future. The project lead has submitted a paper to the HEA STEM Conference in April to promote the project and its findings and 5 adopters (Newcastle College, Bradford, Birmingham, UWE and Manchester) will be trialling the process in their own institutions in the coming months. The project will next look to develop case studies of good practice and recommendations for improvements at module and degree level, provide a portfolio of resources (toolkit) to enable other HEIs to undertake a student-led audit of their degree programmes and evaluate the effectiveness of the toolkit in its implementation.

The University of Bath-led project on exploring employers’ expectations and requirements for STEM students’ writing skills concluded in September 2011. The project mapped current writing skills development practices across SW HEIs and worked in strong collaboration with experts from the universities of Exeter, Plymouth, UWE, Limerick, Oxford Brookes and Coventry. Recommendations have been made to enhance student writing skills, based on project research findings from online survey responses completed by both placement students (59, 38% response rate)  and placement supervisors (43 employers, 54% response rate). A project conference, attended by 45 delegates (more details provided under Specific Aim 5), was held on 12th September 2011 to share project findings and disseminate models for enhancing students’ writing skills, both to specific STEM subjects and more generally across disciplines. Although the project has finished, development and dissemination of the lessons learnt about good practice in writing development in STEM disciplines continues: through the SW Spoke project webpages; two follow up workshops as part of the CD SIG (Manchester Metropolitan University, 24th November 2011 and Bath 16th February 2012); continuation and expansion of the project group as a SIG and a project-themed edition of the Journal of Learning Development in Higher Education.

The ‘Get STEM working: innovation with employer and student engagement’ HLS Regional Action Plan project involving sub-project leads from six HEIs are collaborating strongly with regular online meetings now that the group is well established. At the University of Bath a brochure has been produced for employers to promote involvement in undergraduate industrial projects from an engineering perspective. The promotional material uses three case studies from an employer-perspective and quantifies the value of student projects to the employers at £15-20k, based on research from within the project. The brochures are being trialled with employers (six to date) for feedback and to investigate how to find and assess suitable prospective employers; what is the population of such employers and how can they best be made aware of these opportunities. The University of Exeter are investigating how different disciplines can best present and manage employer-led projects within science by learning from practice within engineering. Seventy 4th year engineering students (having undertaken a third year industrial project) were surveyed to identify relevant industrial links. More information is being sought with eight students identified as having potentially relevant information. Interviews with staff to obtain their perceptions on employer-led projects are continuing, and interviews of engineering projects supervisors are complete.

Bournemouth University are also engaging with a range of employers within engineering and manufacturing with interviews, which have been analysed in readiness for a toolkit of guidelines for HEIs wishing to engage with employers will now be worked on and trialled with six employers who do not currently collaborate with HEIs.

At the University of Bristol, 11 community projects with eight different Bristol-based partners suitable for 3rd and 4th year engineering students have been identified; the first of their kind at the institution. Academic supervisors were secured for the projects and a total of five groups of 3rd and 4th year students are currently undertaking four projects.

With support of the RSC, students at the University of the West of England successfully presented group work to panels of employers (GlaxoSmithKline, Mass Spec Analytical and Avon & Somerset Police, Applied Enzyme Technology, Indigo Science), via different videoconferencing systems on analytical chemistry techniques. The presentations were universally commended by the employer panels and preliminary feedback from the employers has shown that they regarded the presentations as directly relevant to their organisations and informative of the abilities of the students, especially with respect to their scientific and communication skills. For future years, at least 12 other companies have been listed also expressing a strong interest in this activity.

Plymouth University have made contact with 130 STEM-wide companies to identify interest in taking chemistry students for summer placements. Of those 24 companies have expressed an interest in taking chemistry students for summer placements (18%) and traditional chemistry employers demonstrated the greatest interest (45%) and engineering the least (2%). Encouragingly, a number (13%) of non-traditional chemistry employers have expressed an interest in taking chemistry students on short-term placement.

The SW Legacy project has set-up sub-projects with a range of key individuals at the University to ensure that institutional awareness and impacts of the project, alongside its subsequent sustainability is maximised. Outputs of the project report into a newly formed Employability and Careers sub-committee of the University Learning, Teaching and Quality Committee, of which the Director of the SW Spoke is chair; thus linking the project formally into the University governance structure and ensuring that outputs are embedded in core institutional practice. Staff involved in the Legacy project meet as a group (2nd meeting planned for 23rd February 2012) so that links are made for future working and so that projects benefit from the expertise of different STEM disciplines.

As part of the SW Legacy Project, STEM students are being supported to enhance their employability skills and increase their exposure to employers. A programme of mainly employer-led Employability Skills sessions is being piloted by Physics, Maths & Physics, Computer Science with Maths, Computer Science 1st year undergraduates, with a view to embed this approach within the curriculum for all Faculty of Science students at the University of Bath. The pilot is mid-way through with positive feedback from employers (Bank of America Merrill Lynch, Accenture, P&G so far) and students (67%) finding the programme beneficial. Further student access to employers has been made available through an online student-led Alumni Mentoring scheme, involving recent graduates in relevant employment. Furthermore, students are trialling an e-portfolio system, Mahara as a method of tracking and reflecting on their employability skills.

To increase effective interactions between employers and the undergraduate curriculum, the Legacy project is investigating how best to promote employer-engagement opportunities to employers. Information has been collated and analysed on University of Bath employer engagement activities within the undergraduate curriculum over the past six years across all science and engineering departments (representing over 200 employers). Findings from the benchmarking information are being supported by interviews with current employers hosting placements (7 complete with a further 20 planned). The benefits and barriers of placements from an employer’s point of view have been reported and will be used as the basis for employer-focussed promotional material. The project is looking to increase interactions with employers as well as enhancing them, approaches to this are being investigated, such as working with other local networking events for relevant, established audiences.

Guidance and frameworks for the Evaluation of Work Placements has been developed in consultation with placement managers across all faculties at the University of Bath, to ensure that staff are well-supported in evaluating whether placements offer suitable learning opportunities for students. To raise awareness of learning objectives in placements and to train staff two complementary half-day workshops for University staff are scheduled for 27th February and 5th March 2012 (Bath).

The disability strand has undertaken surveys (~25% response rate of ~150 surveyed) on perspectives of placement provision (of pre-entry, current students and 2011-graduates with a declared disability and HE placement staff). Further analysis of responses is being carried out, alongside research with practitioners, to develop materials for staff CPD in supporting placement students identifying with Asperger’s Syndrome.

Undergraduate “Industry Team Projects” have been trialled in the Department of Physics, University of Bath, in conjunction with Visteon Corporation. New module descriptions have been created, and these projects have been formally approved for inclusion within the final year of all the Department’s degree programmes.

Specific Aim 4: Undertake activities to encourage those currently within the workforce and society to engage with further study to develop enhanced knowledge and skills and support enhanced engagement of employers with HE sector activity.

Since July 2011, excellent progress has been made on the “Hydrographic Academy: Meeting the needs of the workforce and industry through innovative flexible online, distance learning” SW Regional Action Plan project. A key achievement of the Hydrographic Academy (HA) team has been completing the Module 1 e-learning materials, and issuing those to the thirteen trial students who are all employees of the project’s industrial partner, Fugro. Trial students have expressed a real enthusiasm about their opportunity to take part with one student writing to the team saying: “The course syllabus looks great! I can't wait to sign up for the first introductory course. Establishing the Hydrographic Academy is a great initiative!”  Students have been requested to fill in an initial questionnaire and make use of the team’s guidance about producing their student video diaries. These video diaries will provide the team with detailed feedback which will be valuable as part of the overall project evaluation process. It is envisaged that the module will take around 8 weeks of part-time study and be finished by the middle of March. This will enable the HA team to analyse the feedback and incorporate it into the final project reporting which will be aimed at disseminating both the project’s methodology of design, delivery and accreditation, and the methodology of developing a successful working partnership between academia and industry.

The team have also started to market and advertise the HA, although this has not been an overt campaign to date. So far, there have been over 50 expressions of interest to register, and the team are receiving an average of 5 registrations a week. Dr Richard Thain, Project Leader, is confident that they will have well over 100 registrations during 2012 for the future iterations of Module 1, once the trial has been completed. Preparations are underway for The Hydrographic Academy’s official launch at a large trade show, Oceanology International in London during March 2012.

The whole HA programme is currently being prepared for academic accreditation by Plymouth University’s Academic Development Committee, and early feedback from this group has been positive. Dr Thain is working towards full accreditation of the programme at both undergraduate and postgraduate levels by the summer of 2012.

Finally, several meetings have been held with the professional bodies regarding accreditation of the HA programme. The Royal Navy kindly facilitated a meeting with the Director of the International Hydrographic Organisation (IHO) at the Naval Dockyard in Plymouth. The HA’s plans were warmly received, and he agreed that his organisation will work closely with the team to ensure that recognition is achieved at the appropriate time.  In November 2011, the Director of the IHO provided the team with a strong letter of support in which he wanted to “congratulate and at the same time to encourage The Hydrographic Academy for this development and the continuity of this effort”. The team have also met with the Chartered Institution of Civil Engineering Surveyors, who have also written a useful letter of support for the HA, and have also agreed at this early stage, that the course should meet their requirements for professional accreditation. A meeting with the Royal Institution of Chartered Surveyors has been set up for March 2012.

The SW Regional Action Plan project, “Progressing from labour market intelligence to HE level provision that is well supported by employers” is being led by the Marchmont Observatory at the University of Exeter, in collaboration with UWE, Weymouth College, University of Plymouth, University of Bath, and Petroc College. The sub-project teams are reviewing their institution’s current approaches to employer engagement and seeking improvements which will lead to an increase and enhancement of ‘employer-led’ provision. Feedback from the sub-project leaders indicates that they are finding the opportunity to discuss with colleagues from different institutions the challenges of employer engagement and possible solutions extremely valuable.

During the last six months the Marchmont Observatory has organised a number of meetings which have facilitated discussions between the partners and external organisations. For example, in November, employer organisations, Cogent and the Engineering Employers Federation, and an employer, TDK Lamda from Ilfracombe, attended a project meeting at Exeter so that partners could get a better understanding of some of the perceptions that these groups hold in relation to responsiveness to employers. Representatives of Dovetail were in attendance at this meeting to record audio content which will feed into the SW Spoke’s Creative STEM website which aims to capture learning emerging from across six regional projects. Another partner meeting facilitated by the Marchmont Observatory involved John Chudley from the National Apprenticeship Service (NAS). It provided a really good opportunity for partners to consider the role that the future direction of higher apprenticeships may be able to play in supporting better routes for employer engagement.

The Marchmont Observatory also completed the planned review of the use partner institutions make of labour market intelligence to inform their engagement with employers. The review used a combination of a questionnaire and more in-depth interviews with key contacts in partner organisations with partners providing up to 10 contacts of those engaged in employer engagement activities. The findings will be written up in report and made available via the South West Spoke website.

Sub-project teams are continuing to make good progress towards meeting the aims and objectives of their individual projects. Each one has involved wide consultation within their own institutions of those involved in the processes around engaging employers and views are being fed into the development of new ways of working and toolkits to support these revised approaches. It is pleasing to see that good practice is being shared between project partners, for example, one partner recently visited another’s institution to look at their particular customer relationship management system. Partners have also undertaken widespread consultation with their local employers via telephone and face-to-face interviews: one partner encouraged 50 local engineering companies to take part in the research and provide information on the composition of their workforces, anticipated growth strategies, training and development and opportunities for working with the University and its partner colleges.

Feedback from employers has highlighted the value of face-to-face communication in building relationships and understanding companies’ needs more fully and the fact that they see a value in FE and HE working collaboratively to establish a single offer.

The University of Plymouth, with support from The Royal Statistical Society Centre for Statistical Education (RSSCE), and in collaboration with Devon County Council, has now completed the project entitled “Enhancing Workplace Statistical Literacy” and is in the process of writing the final case study report. One of the aims of the project was to compare blended learning and an entirely web-based approach to delivering the course. Feedback from the 24 employees from the Fire and Rescue Authority who took part in the first trial showed a preference for face-to-face discussions, and a great reluctance to put ‘opinions’ and ‘guesses’ on an electronic system. Some remodelling of the material took place before the second trial, but it was found that there were concepts within the course which required the type of discussion which it was not possible to facilitate online. The interactive course material and trainers’ manual outlining the blended approach to learning that worked best will be made available on an ongoing basis through the RSSCE’s website and promoted as part of their activities.

The team received positive feedback from employees about what they had learnt through the course and Devon County Council are now delivering Critical Appraisal Skills courses which cover many of the key aspects of statistical literacy. As a result of its work with Plymouth University, Devon County Council is planning to continue to expand its provision of critical appraisal courses to partner organisations in the South West. In addition, elements of the workbased course are now being used within undergraduate courses at Plymouth University and within a “Teaching Statistical Literacy” module of the PGCAP course for new lecturers.

Facilitated through the PTA scheme, the course material is now being adapted by Coventry University for their employer base, with support from Paul Hewson at Plymouth University. It will then be added to Coventry University’s existing external short course CPD portfolio and marketed by the CPD team. The first meeting between project leaders to facilitate the adoption process took place at the beginning of January 2012.

The project led by the University of the West of England focusing on enhancing nurses’ numeracy skills is making good progress. The University’s virtual patient was already under development at the beginning of the project and this presented the opportunity to adapt this tool so that it can be used for the application of clinical scenarios related to numeracy.  The first stage of adapting the DEWIS e-assessment system for nursing and midwifery students is almost complete and the team are in the final stages of agreeing the numeracy DEWIS software feedback. This process has proved to be more challenging than expected, which resulted in some medical prescribers being brought in to assist. However, the online numeracy drug application has now been completed and the team will be in a position to run the pilot in February 2012. The Project Leader has reported that the collaborative working between the Department of Nursing and Midwifery and the Department of Mathematics that this project has encouraged is having positive benefits on other aspects of the Departments’ work through the stronger working relationships forged.

Plans are underway for the SW Spoke’s Workforce Development and Employability Conference at Sandy Park Conference Centre near Exeter on Monday 18th June 2012. The aim is to showcase outputs from the Spoke’s workforce development and employability projects to regional employers and the HE and FE STEM communities. The Royal Academy of Engineering, the Institute of Maths and Its Applications and the Nuclear Island project in the SW have already agreed to have exhibition stands at the event. The Regional Steering Group have been asked to recommend Research Centres in their own institutions which may be of particular interest to employers who may be interested in having an exhibition stand, for example the University of Exeter’s Centre for Additive Layer Manufacturing.

Specific Aim 5: Disseminate good practice and information and stimulate its wider uptake based upon collaboration and the sharing of ideas.

The Spoke’s website (http://www.hestem-sw.org.uk/) has seen a huge increase in usage over the past 6 months. It has received 7,901 visits (up from 3,327 in the previous 6 months) from 4,550 visitors (up from 1,743). These visitors have made 29,105 page views (up from 17,412). The website remains a key dissemination tool for regional projects – all project reports and outputs are hosted on it, alongside information on best practice, funding news and events.

A range of project events have been held to disseminate good practice from Spoke projects:

- The ‘Developing Writing in STEM Disciplines’ project (cross-reference Specific Aim (3)) concluded in September 2011 with a project conference at Bath attended by some 45 people. The delegates were a rare mix of subject specialists, learning developers, writing developers, Careers Advisors, librarians and English Language Centre staff; some had travelled from as far away as the Republic of Ireland. All conference outputs are available online. As a direct result of the conference, plans are underway to launch a Special Interest Group in STEM writing and to publish in a peer-reviewed journal. The project lead has also been involved in delivering two related Curriculum Development SIG workshops to some 20+ attendees.

- The ‘STEM Communicator Models’ project (cross-reference Specific Aim (2)) held a ‘Student Involvement in STEM Activities’ workshop at the University of Bath on Monday 14th November 2011. Over 40 HE STEM practitioners from across the UK attended to discuss and compare good practice in student involvement in STEM outreach schemes and to hear more about the project’s evaluation of student motivations for undertaking STEM activities. The event was well received, as evidenced by the following comments from attendees: “It was really useful to identify the employability skills that students develop from outreach activities and to understand better the motivations of students to do outreach work;” “I hoped to find out more about what other institutions are doing in this area to share good practice. I feel that I have done this.” All workshop outputs are available online. In addition, the project leads presented project findings at the NCCPE’s annual conference in Bristol at the end of November 2011, with delegates once again feeding ideas into the planned Guide.

- The ‘Community of Practice for STEM Outreach Practitioners’ project (cross-reference Specific Aim (2)) held the second of three events on Wednesday 2nd November 2011 at @Bristol Science Learning Centre. Attracting some 35 STEM outreach practitioners from a range of sectors and from across the region and beyond, the event provided an opportunity for delegates to have hands-on experience of a range of outreach materials produced by the professional bodies. The event also included contributions from nationally recognised speakers in the field of outreach including Wes Streeting, Chief Executive of the Helena Kennedy Foundation and Dr Graeme Atherton, Director of AccessHE.

- The Transition & PAL projects (cross-reference Specific Aim 2) held the second of four seminars on Wednesday 23rd November 2011 at the University of the West of England. The seminar focused on PAL and in particular, on some research into online models of PAL that are being undertaken by the project. Attended by over 30 delegates (an increase in numbers from the first seminar in June) from across the SW and beyond, the seminar was followed up by a briefing paper with a print run of 1,500 copies that were disseminated across relevant national and regional contacts. The seminar was well-received with comments including: “I learned that people are doing it and that there are lots of good ideas for replication, as well as enthusiastic colleagues. It makes the fact that (institution name) is coming from behind a lot easier to deal with because ‘fixing it’ needn’t be difficult;” “I’ve emailed several people since the event and hope to get some more ideas to start to develop the online resources we have.”

Five SW projects have been ‘adopted’ through the PTA scheme by 20 adopters from across the country. Adoption processes are now underway and evaluations from each adopter will be complemented by meta-evaluations by each custodian to ensure that learning is captured and maximised.

Capture for the SW Spoke’s innovative creative learning journeys (CLJs) continues, with all captures planned for completion by the end of March 2012. Outputs captured to date can be viewed via the CLJ website at www.creativestem.co.uk. A meeting between relevant project leads, the SW Spoke and Dovetail (the company hired to produce the CLJs) took place on 10th January 2012 to: identify progress and challenges to date; comment on and improve the CreativeSTEM website and plan dissemination of the CLJs once they are complete. The Programme’s Dissemination Officer attended the event to help ensure that promotion of CLJs is maximized following final captures.

Working with the Midlands & East Anglia Spoke, the SW Spoke has co-led the Curriculum Development SIG. Seven workshops have been arranged to take place across the country, covering the cross-disciplinary issues of: e-assessment; student-led projects; community engaged learning and writing and employability skills. The first workshop, on writing and employability skills, took place at Manchester Metropolitan University on 24th November 2011. Despite attracting only 8 delegates, it resulted in useful discussions and a bid to the national programme to establishing a Writing Skills SIG to develop the discussions further. The remaining six workshops are to take place across February and March 2012, with 110 delegates having registered to date.

Since November, institutional seminars have been held at: Exeter, Bournemouth, Plymouth and Bath universities. These seminars, organized by institutional contacts, have involved respective HE STEM project leads disseminating information about their projects to colleagues within their institution. There has been high-level buy-in to the seminars, with regional steering group representatives introducing their institution’s seminar. Over 120 people have been reached through these seminars; with the production of marketing and promotional materials linked to seminars, awareness of HE STEM projects across institutions has been raised considerably.

The SW Spoke has continued to develop and strengthen its links with key organisations across the region, particularly STEMNET and the National Coordinating Centre for Public Engagement (NCCPE). Both organisations are funded until at least 2015, and so their adoption and adaption of project outputs will enhance sustainability. In the case of STEMNET, eight of the SW’s funded projects have outputs of relevance to their work (STEMNET are involved on the steering groups of five of these projects). The Widening Participation & Curriculum Development Officer met with Kirsten Bodley (Chief Executive of STEMNET) in August 2011, and Kirsten has pledged her full support to helping promote relevant outputs around their networks. Following this up, the Spoke is now in contact with Kat Sandford (STEMNET Ambassadors’ Programme Manager) to promote relevant outputs. As well as delivering the Outreach Evaluation PTP and designing a workshop on Community Engaged Learning for the CD SIG, the Director of the NCCPE (Paul Manners) has committed to hosting relevant outputs from regional projects on their website following the programme close.

Specific Aim 6: Ensure an efficient, effective, adaptable Programme that is well managed and responsive to emerging sector needs and priorities.

The SW spoke has continued to provide support to project partners, through attendance at project steering group meetings, regular contact and in-depth feedback on project progress reports, webpage presence through the SW Spoke website and increasingly, at this stage in the programme, events. As well as supporting project development, the team ensure that projects are well linked to other relevant HE STEM projects inside and outside the region, encouraging collaboration and allowing partners to identify with the Programme more extensively.

Project leads from different projects at different HEIs have started to work together to the benefit of their HE STEM Higher Level Skills projects through introductions made by the SW Spoke. Through the South West External Advisory Group meetings (see below), project leads with complementary interests in employer engagement have linked up, bringing not only their two projects together but also the 12 subprojects integral to their work. The SW Spoke is organising a meeting (7th February 2012) of these project leads to build on this connection and to facilitate their future collaborative plans, which will also involve other HE STEM employer engagement related projects in the SW. The region’s online, private, project collaboration tool continues to be an important method of sharing up-to-date information within projects and with full access to the each project area, the Spoke can continually recognise potential alignments with other projects.

The second of three meetings of the South West External Advisory Group took place over a full day in October 2011. The Group was established as part of the SW Spoke’s strategy for managing and monitoring its Higher Level Skills regional projects, and in order to gain the perspectives of experts in the field who are not directly involved in the projects or members of the institutions involved.  Members of the Group include a Training Manager from a large local engineering company, representatives of employer organisations, the Director of Universities South West, a member of HEFCE’s Exchange Group and Programme Manager from JISC. At the October meeting project leaders from the South West’s three large-scale Higher Level Skills projects and the Legacy Project presented formally on progress made since the June meeting. The Group was able to advise on specific areas of the projects, for example, recommending where individual project leader’s would find examples of existing customer relationship management systems and good practice in developing workforce development programmes, as well as providing feedback on planned approaches to evaluation which will be of value to all project leaders present. It became clear at the October meeting that it is particularly valuable that members of the Group have experience of previous projects in the South West focusing on employer engagement, for example, the Higher Level Skills Pathfinder Project.

To further investigate how projects may benefit from working together, we have invited all project leads and their respective steering groups to attend a day meeting on ‘Sustaining a Legacy’ (23rd April) to look at ways that Communities of Practice that already exist from within the programme can be sustained and built upon, and to identify any new potential networks amongst project partners attending (confirmed speaker: Dr Juliet Millican, Community University Partnership Programme). Support from the National Programme will underline the importance of project sustainability and dissemination. Furthermore the meeting will allow the Spoke to receive feedback on the processes used within the Programme and synthesise this information for Spoke-level evaluation.

To aid transparent transferability and dissemination of project materials, the SW Spoke hosted and evaluated a SCORE/ JISC Legal Creative Commons (CC) and Open Educational Resource (OER) on 12th December 2011 (16 attendees). The event was funded by the Hub and duplicated in other regions. Feedback from the delegates showed that there was a need for more practical guidance on CC licences, and as such, the SW Spoke developed a brief practical guide on Adding Creative Commons Licences to your materials which has been provided to the event facilitators to add to their suite of CC materials.

To facilitate an efficient and effective programme across the SW, sustainability and evaluation strategies from earlier within the programme have been built upon. For example, Evaluation Guidance was developed for the SW, using SW good practice examples in response to common feedback provided to project leads in the region, following the completion of evaluation templates required by the National Programme. This synthesis of evaluation information from the templates, by the SW Spoke, resulted in a higher level understanding of projects in the region, which is very applicable across the whole Programme. The Evaluation Guidance was championed by the Programme Director at the 5-6th January 2012 Programme Evaluation Conference (Birmingham) and it is envisaged that wider circulation will be beneficial.